## Sheet1
Record ID | Event time | Area | Observation | Expected condition | Measured / actual | Severity | Immediate action | Evidence status | Owner | Due date | Open question
QI-001 | 2026-09-17 08:15 | Fermentation | Foam level rose above normal operating band during hour 11. | Foam below 65% sight-glass level. | 78% for approximately 14 minutes. | High | Feed rate reduced by 8%; antifoam dose applied within current instruction. | Operator log available | Shift Lead | 2026-09-18 | Was the antifoam dose independently verified?
QI-002 | 2026-09-17 08:22 | Process control | Dissolved oxygen sensor showed intermittent spikes. | Stable 28%-35% during phase 3. | Readings ranged 24%-48%. | Medium | Secondary handheld reading requested. | Trend export available; handheld record missing | Automation Engineer | 2026-09-18 | Was this sensor calibrated before the batch?
QI-003 | 2026-09-17 09:05 | Raw material | Nutrient lot NM-448 used after a warehouse temperature excursion. | Store at 15-25 C. | Recorded at 29.4 C for 3 h 10 min two days earlier. | Critical | Lot placed on hold after batch completion; deviation linked. | Temperature logger available | Warehouse Quality | 2026-09-17 | Who approved release of NM-448 for use?
QI-004 | 2026-09-17 10:40 | Quality control | In-process viscosity result exceeded preliminary alert limit. | Alert limit 420 cP. | 447 cP; duplicate test not recorded. | High | Sample retained; batch continued pending review. | Single worksheet available | QC Supervisor | 2026-09-18 | Was a duplicate test performed and was the method current?
QI-005 | 2026-09-17 12:10 | Documentation | Electronic batch record contains an 18-minute gap in agitation entries. | Automated entry every minute. | No entries from 11:42 to 12:00. | Medium | IT ticket opened; historian data requested. | Ticket exists; historian extract pending | MES Support | 2026-09-19 | Was agitation uninterrupted during the data gap?
QI-006 | 2026-09-17 15:30 | Sampling | Final sample label has handwritten correction without countersignature. | Corrections signed and dated. | Original sample time changed from 14:50 to 15:05. | High | Sample quarantined from release testing. | Photo available | Lab Coordinator | 2026-09-18 | Who made the correction and why?
QI-007 | 2026-09-18 09:00 | Investigation | Preliminary review mentions pump P-204 vibration. | Vibration under 4.5 mm/s. | No numerical vibration value included. | Medium | Maintenance inspection requested. | Work order open | Maintenance Lead | 2026-09-20 | Could pump variation explain oxygen and foam changes?
QI-008 | 2026-09-18 11:20 | Batch disposition | No final impact assessment completed. | Quality impact assessed before release decision. | Batch status: on hold. | Critical | Cross-functional review scheduled. | Pending | Quality Head | 2026-09-20 | What evidence is needed to decide disposition?